## Backlog
ID | Phase / Tier | Category | Feature | Description | Status | Priority | Effort | Inspired By | Dependencies | Notes
P0.1 | Phase 0 | Infra | Fix docker-compose.yml | Broken volume mount + blank port entry — make Postgres persist cleanly. | Done | Critical | S | Custom
P0.2 | Phase 0 | Infra | Flyway dep + config | Add flyway-core / flyway-database-postgresql, baseline-on-migrate=true. | Done | High | S | Custom |  | V1__init.sql still TBD
P0.3 | Phase 0 | Infra | ddl-auto → validate | Switch Hibernate to validate once V1 baseline captured. | Deferred | High | S | Custom | P0.2,TEST4 | Blocked on V1 dump
P0.4 | Phase 0 | Testing | Testcontainers + sanity ITs | AbstractIntegrationTest + HealthControllerIT + AccountRepositoryIT. | Done | High | M | Custom
P0.5 | Phase 0 | Infra | GitHub Actions CI | mvn verify + npm build on push / PR. | Done | High | S | Custom | P0.4
P0.6 | Phase 0 | Docs | Sync README with 13 modules | README listed only auth/health/bot — refresh to reality. | Done | Medium | S | Custom
P0.7 | Phase 0 | Infra | Port consolidation 5185/8185/5485 | All app ports end in -185 to avoid collision with other local apps. | Done | Low | S | Custom
P1.1 | Phase 1 | Bot Core | BrowserTravianClient stable login | Tolerant selectors + humanType, retry, captcha-aware fallback. | Done | Critical | L | TravBotSharp
P1.2 | Phase 1 | Bot Core | Village scraping scheduler | VillageScrapeScheduler refreshes resources/buildings on cadence. | Done | Critical | M | TravBotSharp | P1.1
P1.3 | Phase 1 | Bot Core | Build queue executor | BuildQueueScheduler picks next pending item, clicks upgrade. | Done | Critical | L | TravBotSharp | P1.2
P1.4 | Phase 1 | Bot Core | NPC trade automation | Marketplace gid=17 NPC redistribute, gated on Plus/gold. | Done | High | M | TravBotSharp | P1.1
P1.5 | Phase 1 | Bot Core | Farmlist runner | FarmlistSendScheduler + sendFarmlist clicks startFarmListRaid. | Done | Critical | M | TravBotSharp | P1.1
P1.6 | Phase 1 | Bot Core | Hero attribute spend | Auto-allocate unspent points into configured attribute. | Done | High | M | TravBotSharp | P1.1
P1.7 | Phase 1 | Bot Core | Auto re-login on 302 | Wrap NotLoggedInException, trigger login(), retry once. | Done | High | S | TravBotSharp | P1.1 | Auto re-login: SessionRecoveryService, opt-in toggle, 10-min cooldown (2026-07-05)
P1.8 | Phase 1 | Bot Core | Hero adventure auto-runner | Pick safest adventure, send hero, track HP. | Not Started | Medium | M | TravBotSharp | P1.6
P1.9 | Phase 1 | Bot Core | Resource overflow alert | Warehouse > 95% → BotEvent + (later) notification. | Done | Medium | S | Custom | P1.2,NOT1 | ResourceOverflowMonitor >=95%, BotEvent WARN + Discord toggle (2026-07-05)
P1.10 | Phase 1 | Bot Core | Master-builder (gold) protection | Refuse to click gold-only upgrade button when queue full. | Done | High | S | Custom | P1.3
P1.11 | Phase 1 | Bot Core | Server time / Plus / UTC offset scrape | Persist offset + Plus status on every dorf1 scrape. | Done | Medium | S | Custom | P1.2
P1.12 | Phase 1 | Bot Core | Sidebar village auto-discovery | Parse sidebar list to upsert villages without manual config. | Done | Medium | S | Custom | P1.2
P1.13 | Phase 1 | Bot Core | In-game build queue parsing | Read finish-at timestamps from #buildingList sidebar. | Done | Medium | S | Custom | P1.2
P1.14 | Phase 1 | Bot Core | Queue reconciliation RUNNING/DONE | Match scraped page state to local queue rows. | Done | High | S | Custom | P1.13
P2.1 | Phase 2 | Safety | HumanDelay range | Pre-action random delay from configurable min/max. | Done | Critical | S | Custom
P2.2 | Phase 2 | Safety | humanType per-key with stalls | Per-char keypress with 60–180 ms cadence + 6% thinking stalls. | Done | Critical | S | Custom
P2.3 | Phase 2 | Safety | Click-or-navigate human nav | Prefer clicking <a> instead of editing address bar. | Done | Medium | S | Custom
P2.4 | Phase 2 | Safety | Multi-account parallel sessions | Per-account browser via BrowserSessionManager + ConcurrentHashMap. | Done | High | S | TravBotSharp
P2.6 | Phase 2 | Safety | Playwright proxy injection | Apply AccountProxy when launching Chromium; rotate per account. | Done | Critical | M | Custom | P2.4 | AccountProxy entity exists but unused · Active AccountProxy row applied at Chromium launch via Playwright proxy options (2026-07-05)
P2.7 | Phase 2 | Safety | Rate limiter per account | Bucket4j or token bucket: cap req/min per accountId. | Done | High | M | Custom |  | ActionRateLimiter: per-account token bucket, maxActionsPerMinute setting (default 20), gates every browser action (2026-07-05)
P2.8 | Phase 2 | Safety | Captcha detect + pause + notif | Detect challenge DOM markers, pause scheduler, notify user. | Done | Critical | M | Custom | NOT1 | CaptchaDetector on dorf1/dorf2 + CaptchaGate pause + session release + Discord notify; manual login resumes (2026-07-05)
P2.9 | Phase 2 | Safety | User-agent / viewport rotation | Per-session UA + viewport randomization at launch. | Done | Medium | S | Custom | P2.4 | BrowserFingerprint: matched UA+viewport pool, randomized per session at context creation (2026-07-05)
P2.10 | Phase 2 | Safety | BotLog UI filters | Frontend filter by account/severity/date/search. | Done | Medium | M | Custom |  | Backend log exists · Bot log filters: outcome/search/date-range, JPA Specifications (2026-07-05)
P2.11 | Phase 2 | Safety | Headless mode toggle per-account | Per-account boolean: run Chromium without UI. | Done | Low | S | Custom | P2.4 | Per-account headless flag on AccountSettings; BrowserSessionManager reads it at launch; toggle in account settings Browser group (2026-07-05)
P2.12 | Phase 2 | Safety | Mouse path randomization | Curve path before click instead of teleporting. | Not Started | Low | M | Custom
A1 | Tier A | AI Analytics | Incoming attack scraper + TS analyzer | Parse rally point, compute attacker speed/troop class. | Done | Critical | L | Travcotools | P1.2
A2 | Tier A | AI Analytics | Return-catch optimizer | Suggest launch-time so we hit attacker home with no defense. | Done | Critical | M | Custom | A1
A3 | Tier A | AI Analytics | Inactive search (map.sql) | Parse daily map.sql dump, flag inactive players with filters. | Done | High | L | Travcotools
B1 | Tier B | Analytics | Farmlist analyzer + traffic-light | Parse berichte.php raid reports, attribute, score per target. | Done | High | L | Travcotools | P1.5
B2 | Tier B | AI Analytics | Enemy intel + hero tracker | Snapshot enemy profile, narrate hero/pop changes. | Done | High | L | Custom | A1,A3
B3 | Tier B | AI Analytics | Cropper finder 15c/9c | Heuristic classification from population + capital flag. | Done | Medium | M | Travmap | A3
C1 | Tier C | Notifications | Discord webhook notifier | Push BotEvents to configured webhook URL. | Done | High | S | Travcotools |  | Was already implemented: DiscordNotifier + settings page + per-event toggles
C2 | Tier C | Notifications | Telegram notifier | Bot token + chat id, push critical events. | Done | Medium | S | Custom |  | TelegramNotifier + settings page, wired via new EventNotifier interface + NotificationDispatcher fan-out (Discord+Telegram) (2026-07-05)
C3 | Tier C | Notifications | Desktop push notifications | Browser Notification API + service worker. | Done | High | S | Custom |  | useIncomingAttackWatch hook: browser Notification API on new incoming attack, gated on desktopNotificationsEnabled, dedup + seed-on-first-poll (2026-07-05)
C4 | Tier C | Coord | Defense pull (wave-timing) | Coordinate sends from N villages to arrive simultaneously. | Not Started | Medium | L | Travcotools | P1.1
C5 | Tier C | Coord | Resource subsidies automation | Inter-account / inter-village marketplace push routing. | Not Started | Medium | M | Travcotools | P1.4
C6 | Tier C | Coord | Sitter coop support | Multi-user access with role permissions. | Not Started | Low | L | Travian
D1 | Tier D | Strategy | Artifact spawn coordinator | Hardcoded spawn dates + grab planning per village. | Not Started | Low | XL | Travcotools
D2 | Tier D | Analytics | Top10 / leaderboard delta tracking | Daily snapshot, render deltas, suspect-hammer detection. | In Progress | Medium | M | Travcotools |  | Entity + scheduler exist; UI partial
D3 | Tier D | Strategy | WW countdown tracker | Wonder-of-the-World construction watcher (very late server). | Not Started | Low | M | Travian
D4 | Tier D | Analytics | Cropper ROI ranking | Score croppers by distance/oasis bonus/settle time. | Not Started | Low | M | Custom | B3
D5 | Tier D | Strategy | Goal mode (WW/off/deff templates) | Pre-set build queues + troop mix based on user goal. | Not Started | Low | XL | Custom | P1.3
D6 | Tier D | Strategy | CP / settler planner | Compute when CP + 3 settlers reach quota for next village. | Not Started | Medium | M | Gettertools | P1.2
D7 | Tier D | Strategy | Capital choice advisor | Detect 15c in radius, recommend capital relocation. | Not Started | Low | M | Travmap | B3
MAP1 | Tier MAP | Map | Interactive world map view | Render MapPlayer/MapVillage on Canvas/SVG, pan + zoom. | Done | High | XL | Travmap | A3 | WorldMapController /servers/{id}/intel/map (join village+player) + Canvas MapPage: pan/zoom, tribe colours, inactive dimmed, capital rings, hover tooltip, coord readout, adaptive grid; route+sidebar+i18n (2026-07-05)
MAP2 | Tier MAP | Map | Layer toggles | Toggle: own villages, alliance, tribe, inactive, croppers. | Not Started | High | M | Travmap | MAP1
MAP3 | Tier MAP | Map | Distance measurement tool | Click 2 tiles → field distance + travel time per tribe. | Not Started | Medium | S | Travmap,Gettertools | MAP1
MAP4 | Tier MAP | Map | Tile action menu | Right-click tile → add to farmlist / mark cropper / view player. | Not Started | Medium | M | Custom | MAP1,B1,B3
MAP5 | Tier MAP | Map | Historical playback (time slider) | Step through map.sql snapshots over time. | Not Started | Low | L | Travmap | MAP1 | Needs MapPlayerHistory entity
MAP6 | Tier MAP | Map | Bookmarks / notes on tiles | Pin tiles with user notes (cropper target, enemy spawn, etc). | Not Started | Low | S | Travmap | MAP1
MAP7 | Tier MAP | Map | Search by player / alliance | Center map on player or zoom-fit alliance territory. | Not Started | Medium | S | Travmap | MAP1
MAP8 | Tier MAP | Map | Map.sql diff visualization | Show newly-settled / abandoned villages between syncs. | Not Started | Low | M | Travmap | MAP1
MAP9 | Tier MAP | Map | Heatmap overlays | Population density / alliance influence heatmap. | Not Started | Medium | M | Travmap | MAP1
MAP10 | Tier MAP | Map | Incoming-attack arrows overlay | Render IncomingAttack source→target arrows live. | Not Started | High | M | Custom | MAP1,A1
CALC1 | Tier CALC | Calculator | Troop battle simulator | Simulate raid: attacker units vs defender + wall + hero. | Not Started | Medium | M | Gettertools
CALC2 | Tier CALC | Calculator | Travel time calc | Coord-to-coord time per tribe / unit class. | Done | High | S | Gettertools |  | TravelCalculatorPage: torus distance, TS bonus, landing-time reverse calc (2026-07-05)
CALC3 | Tier CALC | Calculator | Settler ETA calc | Resources + CP + production → ETA new village. | Not Started | Low | S | Gettertools | P1.2
CALC4 | Tier CALC | Calculator | Hero regen calc | HP regen rate from helmet / production bonus. | Not Started | Low | S | Gettertools | P1.6
CALC5 | Tier CALC | Calculator | Building cost lookup | Lookup wood/clay/iron/crop cost for any building level. | Not Started | Medium | S | Gettertools
CALC6 | Tier CALC | Calculator | Combat simulator (advanced) | Includes hero stats, walls, alliance bonuses, morale. | Not Started | Low | L | Gettertools | CALC1
NOT3 | Notifications | Notifications | Sound alerts on critical events | Web Audio API on incoming attack, captcha, hero died. | Done | Medium | S | Custom | C3 | Web Audio two-tone beep on new incoming attack, gated on new soundAlertsEnabled setting, wired into useIncomingAttackWatch (2026-07-05)
NOT4 | Notifications | UX | WebSocket / SSE live updates | Push backend events to UI instead of polling REST. | Done | High | M | Custom |  | SSE: SseEventBroadcaster + /api/events/stream; broadcasts bot-event + incoming-attack after commit; frontend EventStream context + useLiveEvent wired into BotLogPage and useIncomingAttackWatch (polls kept as fallback) (2026-07-05)
NOT5 | Notifications | UX | Mobile-friendly responsive layout | Sidebar collapses, tables horizontal-scroll, touch targets. | Not Started | Low | M | Custom
NOT6 | Notifications | UX | PWA install | Service worker + manifest, installable on mobile/desktop. | Not Started | Low | S | Custom | NOT5
NOT7 | Notifications | Notifications | Email daily digest | SMTP / Resend summary of activity & alerts. | Not Started | Low | M | Custom
SEC1 | Security | Security | Password encryption AES-GCM | Encrypt Account.password at rest keyed from master password. | Not Started | Critical | M | Custom |  | Currently plaintext
SEC2 | Security | Security | Session secret rotation | Refresh Travian session cookies periodically. | Not Started | Low | S | Custom | P1.1
SEC3 | Security | Security | Audit log of account access | Track who/when accessed Account credentials. | Not Started | Low | S | Custom
SEC4 | Security | Security | IP allowlist for backend API | Restrict /api/* to allowed IPs (when deployed). | Not Started | Low | S | Custom
REL1 | Reliability | Reliability | Durable task queue | Persist scheduler state in DB so restart resumes mid-batch. | Not Started | High | L | Custom |  | task/ module exists, not wired
REL2 | Reliability | Reliability | Crash-recovery state | On boot, finish or rollback in-flight Playwright operations. | Not Started | High | M | Custom | REL1
REL3 | Reliability | Reliability | PG dump scheduler | Daily backup, retain N copies. | Not Started | Medium | S | Custom
REL4 | Reliability | Reliability | Health-check + auto-restart | /api/health watchdog + supervisor restart on failure. | Not Started | Low | S | Custom
REL5 | Reliability | Reliability | Observability (Prometheus + Grafana) | Metrics export + dashboards. | Not Started | Low | L | Custom
PERF1 | Performance | Performance | HTTP fallback client | Jsoup + HttpClient + cookies for routine scraping (no browser). | Not Started | High | XL | Custom | P1.1 | 10x faster, 5x less RAM
PERF2 | Performance | Performance | Page result caching | Cache scraped HTML for N seconds for repeated reads. | Not Started | Low | M | Custom
PERF3 | Performance | Performance | Browser pool optimization | Reuse Chromium contexts across accounts where safe. | Not Started | Medium | M | Custom | P2.4
TEST1 | Testing | Testing | Scraper golden HTML fixtures | Convert build/debug/*.html into parser regression tests. | Done | High | M | Custom |  | Top10PageParserTest: real captured statistics page fixture (4 categories x10 rows) + synthetic edge cases; passes in Maven container (2026-07-05)
TEST2 | Testing | Testing | Frontend E2E tests | Playwright tests for sidebar / pages / forms. | Not Started | Medium | L | Custom
TEST3 | Testing | Testing | Load testing | Simulate N accounts × M villages traffic. | Not Started | Low | M | Custom
TEST4 | Testing | Testing | V1 baseline migration generation | Run Hibernate schema export → V1__init.sql. | Not Started | High | S | Custom | P0.2 | Blocks P0.3
I18N1 | i18n | i18n | English translation | All UI strings keyed. | Done | Critical | S | Custom
I18N2 | i18n | i18n | Croatian translation | All UI strings keyed. | Done | Critical | S | Custom
I18N3 | i18n | i18n | German translation | Important market for Travian. | Not Started | Low | M | Custom
I18N4 | i18n | i18n | Russian translation | Important market for Travian. | Not Started | Low | M | Custom

## Summary
Travian-Ultimate Roadmap Summary
By Status |  |  | By Priority
Status | Count | % of Total | Priority | Count | % of Total
Done |  |  | Critical
In Progress |  |  | High
Deferred |  |  | Medium
Not Started |  |  | Low
Total
By Inspiration |  |  | Progress by Phase / Tier
Source | Count |  | Phase / Tier | Done | Total | % Done
TravBotSharp |  |  | Phase 0
Travcotools |  |  | Phase 1
Travmap |  |  | Phase 2
Gettertools |  |  | Tier A
Custom |  |  | Tier B
Tier C
Tier D
Tier MAP
Tier CALC
Notifications
Security
Reliability
Performance
Testing
i18n

## Legend
ROADMAP.xlsx — Column & Value Legend
Status values
Value | Meaning
Done | Implementation complete; in production.
In Progress | Some scaffolding present; not feature-complete.
Deferred | Blocked or intentionally postponed; reason in Notes.
Not Started | Backlog item, not yet picked up.
Priority values
Value | Meaning
Critical | Blocks core flow or security; do first.
High | Materially improves UX / safety / coverage.
Medium | Quality-of-life or strategic edge.
Low | Nice-to-have / polish.
Effort values
Value | Meaning
S | Small (≤ 1 day)
M | Medium (1–3 days)
L | Large (3–7 days)
XL | Extra Large (> 1 week)
Inspired By values
Value | Meaning
TravBotSharp | Local desktop bot — autoplay parity.
Travcotools | Cloud planner — attack/defense/intel parity.
Gettertools | Pure calculators — troop/travel/cost lookup.
Travmap | Interactive world map viewer.
Custom | Original idea not present in inspirations.
Travian | Mirrors a stock feature of the game itself.
Workflow
Value | Meaning
Add new item | Append a row in Backlog; ID convention: <Phase>.<number> or <Tier><number>.
Update status | Change the Status cell; Summary recalculates on save (LibreOffice / Excel).
Mark blocked | Set Status=Deferred and explain in Notes.
Track dependency | List the blocking IDs comma-separated in Dependencies.